TIMELINE 7 HARI TERAKHIR

Sprint Final — Pengembangan BeasiswaKu
Kelompok 5B — 20 May 2026

Anggota Kelompok

| Nama | NIM | Role | Progress Saat Ini |
| --- | --- | --- | --- |
| Ibrahim Syauqi | L0224019 | Backend A | Baru mulai — ambil 6 task backend |
| Jimly Syahbatin | L0224033 | Backend B | Baru mulai — ambil 6 task backend + security |
| Nadhifa Sakha Tri Yasmin | L0224036 | Frontend A + Backend | 21 task selesai — sisa 4 task frontend |
| Kayla Maharani Muzaki | L0224050 | Frontend B | 7 task selesai — sisa 7 task admin FE |

Progress yang Sudah Selesai

Nadhifa — Backend A + Frontend A (21 task)

| Area | Detail |
| --- | --- |
| Backend Auth (9 endpoint) | register, login, logout, verify-email, resend-verification, forgot-password, reset-password, refresh-token, getMe |
| Backend Profile | GET/PATCH /users/:id/profile — jsonb + progress % + biodata_complete |
| Backend Program | GET /programs (list) + GET /programs/:id (detail) |
| Backend Aplikasi (5 endpoint) | POST create, GET /my (list user), GET /:id (detail), GET / (list admin), PATCH /:id/status |
| Backend Dokumen (4 endpoint) | GET list, POST save, POST upload-url (signed), PATCH status |
| Schema Database | Semua tabel: users, profiles (jsonb), programs, applications, documents, audits, evals, fund_reports |
| Restruktur Route | /api/v1/auth, /users, /programs, /applications — sesuai TSD |
| Cleanup | Hapus file orphan, fix nominal→monthly_amount, standardisasi response {success, message, data} |
| Frontend Student (6 halaman) | Landing, Register, Login, Verifikasi Email, Dashboard, Biodata (single form), Pengajuan (4-step wizard) |
| Auth Frontend | AuthContext (token, protected route, role redirect, auto-logout) |

Kayla — Frontend B Admin (7 task)

| Area | Detail |
| --- | --- |
| Shared Components | Button, Input, Card, Modal, Table, Badge, Loading, Pagination, StatusBadge, SearchBar |
| Layouts | AdminLayout (Sidebar + Header), SiswaLayout |
| Halaman Admin (2) | Admin Dashboard (card stat), Daftar Pengajuan (list + filter + detail 5 tab + status badges) |

Pembagian Sisa Tugas (7 Hari)

| No | Task | PIC | Dibantu | Keterangan |
| --- | --- | --- | --- | --- |
| 1 | Program CRUD backend (POST/PATCH/DELETE) | Ibrahim | Nadhifa | Pola existing dari GET program |
| 2 | Admin Verify API (setuju/revisi/tolak) | Ibrahim | Nadhifa | PATCH /:id/status sudah ada, tinggal tambah rute admin |
| 3 | Fund Report Verify API | Ibrahim | Nadhifa |  |
| 4 | Status Endpoint (timeline 6 tahap) | Ibrahim | Nadhifa |  |
| 5 | SA Dashboard API (4 KPI agregat) | Ibrahim | Nadhifa |  |
| 6 | Seed Data (10+ dummy siswa) | Ibrahim | — |  |
| 7 | Selection Engine (scoring algorithm) | Jimly | Nadhifa | skor = akad*w1 + eko*w2 + prest*w3 + dok*w4 |
| 8 | Ratify API (massal + rollback) | Jimly | Nadhifa |  |
| 9 | Audit Log API (filter + export) | Jimly | Nadhifa |  |
| 10 | Evaluasi API (KPI score) | Jimly | Nadhifa |  |
| 11 | Security final (rate limit, helmet, CORS) | Jimly | — |  |
| 12 | Verify Modals FE (AdminPengajuanPage) | Kayla | — | Sambung dari existing page |
| 13 | Selection Page FE (4 slider + ranking) | Kayla | — |  |
| 14 | Ratify Dialog FE (irreversible warning) | Kayla | — |  |
| 15 | Fund Report Verify UI | Kayla | — |  |
| 16 | SA Dashboard FE (KPI + Recharts) | Kayla | — |  |
| 17 | Audit Log Page + Evaluasi Page | Kayla | — |  |
| 18 | Status Tracking Page (timeline 6 tahap) | Nadhifa | — |  |
| 19 | Forgot Password Page + fix sidebar link | Nadhifa | — |  |
| 20 | Loading skeletons + error boundaries | Nadhifa | — |  |
| 21 | E2E Testing | ALL | — | Hari ke-6 |
| 22 | Demo Script + Screenshots | ALL | — | Hari ke-7 |

Timeline 7 Hari Terakhir

Day 1 — Backend Admin + Status Tracking FE

| Person | Task | Target |
| --- | --- | --- |
| Ibrahim | Program CRUD: POST/PATCH/DELETE /programs | Selesai |
| Jimly | Audit Log + Evaluasi API (GET /super-admin/audit-log, /evaluations) | Selesai |
| Nadhifa | Status Tracking Page (timeline visual 6 tahap) | Selesai |
| Kayla | Verify Modals + integrasi PATCH status | Selesai |

Day 2 — Verify API + Selection Engine

| Person | Task | Target |
| --- | --- | --- |
| Ibrahim | Admin Verify API + Fund Report Verify API | Selesai |
| Jimly | Selection Engine: POST /admin/selections/calculate | Selesai |
| Nadhifa | Forgot Password Page + fix sidebar link | Selesai |
| Kayla | Selection Page (4 slider bobot + ranking table) | Selesai |

Day 3 — Ratify + SA Dashboard + Fund Report FE

| Person | Task | Target |
| --- | --- | --- |
| Ibrahim | SA Dashboard API (GET /super-admin/dashboard) | Selesai |
| Jimly | Ratify API: POST /admin/selections/ratify | Selesai |
| Nadhifa | Loading skeletons + error boundaries | Selesai |
| Kayla | Ratify Dialog + Fund Report Verify UI | Selesai |

Day 4 — SA Dashboard FE + Seed Data + Security

| Person | Task | Target |
| --- | --- | --- |
| Ibrahim | Seed Data (10+ dummy siswa berbagai status) | Selesai |
| Jimly | Security: rate limiting, helmet, CORS, input sanitasi | Selesai |
| Nadhifa | Polish responsive + error handling halaman student | Selesai |
| Kayla | SA Dashboard FE (4 KPI cards + Recharts) | Selesai |

Day 5 — Audit Log + Evaluasi FE + Final Integration

| Person | Task | Target |
| --- | --- | --- |
| Ibrahim | Bugfix & final review semua API | Selesai |
| Jimly | Bugfix & final review backend admin/SA | Selesai |
| Nadhifa | Integrasi frontend student dengan semua endpoint baru | Selesai |
| Kayla | Audit Log Page + Evaluasi Page (KPI) | Selesai |

Day 6 — E2E Testing + Bug Bash

| Person | Task | Target |
| --- | --- | --- |
| Ibrahim + Nadhifa | E2E student: register → profile → apply → track → disbursement → report | Selesai |
| Jimly + Kayla | E2E admin: verify → selection → ratify → fund verify → SA dash | Selesai |
| ALL | Bug bash — catat & fix semua issues prioritas | Selesai |

Day 7 — Final Polish + Presentasi

| Person | Task | Target |
| --- | --- | --- |
| ALL | Fix bug hasil bash | Selesai |
| Ibrahim | Demo script backend | Selesai |
| Jimly | Demo script admin/SA | Selesai |
| Nadhifa | Screenshots student pages + kompilasi UI | Selesai |
| Kayla | Screenshots admin/SA pages + export demo | Selesai |

Catatan

• Ibrahim & Jimly mulai dari 0 — tugas backend mereka adalah endpoint yang belum ada sama sekali

• Nadhifa & Kayla tinggal menyelesaikan frontend yang belum, plus membantu review backend

• Prioritas utama: Selection Engine (Day 2) dan Ratify (Day 3) — critical path untuk frontend Kayla

• File spec acuan: UML Class Diagram, Mockup, SRS (keamanan), FSD (fitur), TSD (endpoint)

• Bobot merata: semua anggota ± 5-7 task dalam 7 hari